## Timeline
Project Information
Protocol No. | {Protocol No}
Initial Start Date | {Today}
Sponsor | {Sponsor}
Other CRO
Vendor
1st Plan ({Today})
Deliverable | Task | Lead | Start Date | Expected Date | Working Day | JNPMEDI Comment | Client Comment
Data Management Plan | Generation of draft | JNPMEDI | 2025-08-04 | 2025-08-07 | 4
| Review of draft | {Sponsor} | 2025-08-08 | 2025-08-11 | 2
| Revision of draft | JNPMEDI | 2025-08-12 | 2025-08-12 | 1
| Finalization | {Sponsor}/JNPMEDI | 2025-08-13 | 2025-08-13 | 1
Blank eCRF | Generation of draft | JNPMEDI | 2025-08-04 | 2025-08-07 | 4
| Review of draft | {Sponsor} | 2025-08-08 | 2025-08-11 | 2
| Revision of draft | JNPMEDI | 2025-08-12 | 2025-08-12 | 1
| Finalization | {Sponsor}/JNPMEDI | 2025-08-13 | 2025-08-13 | 1
DB Spec & Annotated eCRF | Generation of draft | JNPMEDI | 2025-08-14 | 2025-08-19 | 3
| Review of draft | {Sponsor} | 2025-08-20 | 2025-08-20 | 1
| Revision of draft | JNPMEDI | 2025-08-21 | 2025-08-21 | 1
| Finalization | {Sponsor}/JNPMEDI | 2025-08-22 | 2025-08-22 | 1
Development Check List/R&P | Generation of draft | JNPMEDI | 2025-08-14 | 2025-08-19 | 3 | DB Spec과 동시 진행 예정입니다.
| Review of draft | {Sponsor} | 2025-08-20 | 2025-08-20 | 1
| Revision of draft | JNPMEDI | 2025-08-21 | 2025-08-21 | 1
| Finalization | {Sponsor}/JNPMEDI | 2025-08-22 | 2025-08-22 | 1
CRF Completion Guideline | Generation of draft | JNPMEDI | 2025-08-14 | 2025-08-22 | 6 | DB Spec과 동시 진행 예정입니다.
Data Validation Specification | Generation of draft | JNPMEDI | 2025-08-25 | 2025-09-01 | 6
| Review of draft | {Sponsor} | 2025-09-02 | 2025-09-03 | 2
| Revision of draft | JNPMEDI | 2025-09-04 | 2025-09-04 | 1
| Finalization | {Sponsor}/JNPMEDI | 2025-09-05 | 2025-09-05 | 1
UAT Preparation | CDMS Config. / Trigger Set-up | JNPMEDI | 2025-09-08 | 2025-09-11 | 4
| CDMS Config. / Trigger Validation | JNPMEDI | 2025-09-12 | 2025-09-16 | 3
User Acceptance Test | 1st UAT | {Sponsor} | 2025-09-17 | 2025-09-18 | 2 | UAT 진행 시 CRF CG에 대한 첫번째 검토 요청을 드릴 예정입니다. 이는 UAT 진행 시 CRF CG에 따라 CDMS 사용 및 데이터 입력을 하실 수 있도록 하기 위함입니다.
| Correction of Finding | JNPMEDI | 2025-09-19 | 2025-09-22 | 2
| 2nd UAT | {Sponsor} | 2025-09-23 | 2025-09-24 | 2
| Correction of Finding | JNPMEDI | 2025-09-25 | 2025-09-25 | 1
| Finalization | {Sponsor}/JNPMEDI | 2025-09-26 | 2025-09-26 | 1 | CRF CG에 대한 최종화도 함께 진행될 예정입니다.
CDMS Go-live | CDMS Final Validation | JNPMEDI | 2025-09-29 | 2025-09-29 | 1 | UAT 진행 중 수정사항에 대해 CDMS에 대한 Final Validation 진행 및 각 문서에 대한 최종화를 진행하기 위한 일정입니다.
| CDMS Go-live Approval | JNPMEDI | 2025-09-30 | 2025-09-30 | 1
Summary
|  |  | Init. Start Date | 2025-08-04
|  |  | Go-live Date | 2025-09-30
|  |  | Total WD | 40
|  |  | Total CD | 57
Formulas:
Expected Date = WORKDAY([Start Date],[Working Day]-1,IF([Lead]="JNPMEDI",INDEX(ANCHORARRAY(Filter!$A3),,1),INDEX(ANCHORARRAY(Filter!$E3),,1)))
Expected Date = NETWORKDAYS(E42,[Expected Date, row above],INDEX(ANCHORARRAY(Filter!$A3),0,1))
Start Date = WORKDAY([Expected Date, row above],1,IF([Lead]="JNPMEDI",INDEX(ANCHORARRAY(Filter!$A3),,1),INDEX(ANCHORARRAY(Filter!$E3),,1)))
Start Date = WORKDAY(E13,1,IF([Lead]="JNPMEDI",INDEX(ANCHORARRAY(Filter!$A3),,1),INDEX(ANCHORARRAY(Filter!$E3),,1)))

## Holiday
Date | Description | Apply to
2023-05-01 | 근로자의 날 | Every Org.
2023-05-05 | 어린이날 | Every Org.
2023-05-29 | 대체공휴일 | Every Org.
2023-06-06 | 현충일 | Every Org.
2023-08-15 | 광복절 | Every Org.
2023-09-28 | 추석 | Every Org.
2023-09-29 | 추석 | Every Org.
2023-07-15 | JNPMEDI Office Closing | JNPMEDI
2023-10-03 | 개천절 | Every Org.
2023-10-09 | 한글날 | Every Org.
2023-12-25 | 성탄절 | Every Org.
2024-01-01 | 새해 | Every Org.
2024-02-09 | 설날 | Every Org.
2024-02-10 | 설날 | Every Org.
2024-02-12 | 설날(대체 공휴일) | Every Org.
2024-03-01 | 삼일절 | Every Org.
2024-04-10 | 22대 국회의원 선거일 | Every Org.
2024-05-01 | 근로자의 날 | Every Org.
2024-05-06 | 어린이날(대체공휴일) | Every Org.
2024-05-15 | 석가탄신일 | Every Org.
2024-06-06 | 현충일 | Every Org.
2024-07-15 | JNPMEDI Office Closing | JNPMEDI
2024-08-15 | 광복절 | Every Org.
2024-09-16 | 추석 | Every Org.
2024-09-17 | 추석 | Every Org.
2024-09-18 | 추석 | Every Org.
2024-10-03 | 개천절 | Every Org.
2024-10-09 | 한글날 | Every Org.
2024-12-25 | 크리스마스 | Every Org.
2025-01-01 | 신정(양력설) | Every Org.
2025-01-27 | 설 임시공휴일 | Every Org.
2025-01-28 | 설날 연휴 | Every Org.
2025-01-29 | 설날 | Every Org.
2025-01-30 | 설날 연휴 | Every Org.
2025-03-03 | 대체공휴일(3·1절) | Every Org.
2025-05-01 | 근로자의 날 | Every Org.
2025-05-05 | 어린이날 | Every Org.
2025-05-06 | 대체공휴일(부처님 오신날) | Every Org.
2025-06-03 | 대통령 선거 | Every Org.
2025-06-06 | 현충일 | Every Org.
2025-07-15 | JNPMEDI Office Closing | JNPMEDI
2025-08-15 | 광복절 | Every Org.
2025-10-03 | 개천절 | Every Org.
2025-10-06 | 추석 | Every Org.
2025-10-07 | 추석 연휴 | Every Org.
2025-10-08 | 대체공휴일(추석) | Every Org.
2025-10-09 | 한글날 | Every Org.
2025-12-25 | 크리스마스 | Every Org.
2025-08-04 | JNPMEDI Office Closing | JNPMEDI
2025-10-24 | JNPMEDI Office Closing | JNPMEDI
2025-11-07 | JNPMEDI Office Closing | JNPMEDI
2026-01-01 | 새해 | Every Org.
2026-02-16 | 설날 | Every Org.
2026-02-17 | 설날 | Every Org.
2026-02-18 | 설날 | Every Org.
2026-03-01 | 삼일절 | Every Org.
2026-03-02 | 삼일절 대체공휴일 | Every Org.
2026-05-01 | 근로자의 날 | Every Org.
2026-05-05 | 어린이 날 | Every Org.
2026-05-24 | 부처님오신날 | Every Org.
2026-05-25 | 부처님오신날 대체공휴일 | Every Org.
2026-06-03 | 전국동시지방선거 | Every Org.
2026-06-06 | 현충일 | Every Org.
2026-07-15 | JNPMEDI Office Closing | JNPMEDI
2026-08-15 | 광복절 | Every Org.
2026-08-16 | 광복절 대체공휴일 | Every Org.
2026-09-24 | 추석 | Every Org.
2026-09-25 | 추석 | Every Org.
2026-10-03 | 개천절 | Every Org.
2026-10-05 | 개천절 대체공휴일 | Every Org.
2026-10-09 | 한글날 | Every Org.
2026-12-25 | 크리스마스 | Every Org.

## Filter (hidden)
JNPMEDI |  |  | SPONSOR/CRO/VENDOR
Date | Description | Apply to | Date | Description | Apply to
2023-05-01 | 근로자의 날 | Every Org. | 2023-05-01 | 근로자의 날 | Every Org.
2023-05-05 | 어린이날 | Every Org. | 2023-05-05 | 어린이날 | Every Org.
2023-05-29 | 대체공휴일 | Every Org. | 2023-05-29 | 대체공휴일 | Every Org.
2023-06-06 | 현충일 | Every Org. | 2023-06-06 | 현충일 | Every Org.
2023-08-15 | 광복절 | Every Org. | 2023-08-15 | 광복절 | Every Org.
2023-09-28 | 추석 | Every Org. | 2023-09-28 | 추석 | Every Org.
2023-09-29 | 추석 | Every Org. | 2023-09-29 | 추석 | Every Org.
2023-07-15 | JNPMEDI Office Closing | JNPMEDI | 2023-10-03 | 개천절 | Every Org.
2023-10-03 | 개천절 | Every Org. | 2023-10-09 | 한글날 | Every Org.
2023-10-09 | 한글날 | Every Org. | 2023-12-25 | 성탄절 | Every Org.
2023-12-25 | 성탄절 | Every Org. | 2024-01-01 | 새해 | Every Org.
2024-01-01 | 새해 | Every Org. | 2024-02-09 | 설날 | Every Org.
2024-02-09 | 설날 | Every Org. | 2024-02-10 | 설날 | Every Org.
2024-02-10 | 설날 | Every Org. | 2024-02-12 | 설날(대체 공휴일) | Every Org.
2024-02-12 | 설날(대체 공휴일) | Every Org. | 2024-03-01 | 삼일절 | Every Org.
2024-03-01 | 삼일절 | Every Org. | 2024-04-10 | 22대 국회의원 선거일 | Every Org.
2024-04-10 | 22대 국회의원 선거일 | Every Org. | 2024-05-01 | 근로자의 날 | Every Org.
2024-05-01 | 근로자의 날 | Every Org. | 2024-05-06 | 어린이날(대체공휴일) | Every Org.
2024-05-06 | 어린이날(대체공휴일) | Every Org. | 2024-05-15 | 석가탄신일 | Every Org.
2024-05-15 | 석가탄신일 | Every Org. | 2024-06-06 | 현충일 | Every Org.
2024-06-06 | 현충일 | Every Org. | 2024-08-15 | 광복절 | Every Org.
2024-07-15 | JNPMEDI Office Closing | JNPMEDI | 2024-09-16 | 추석 | Every Org.
2024-08-15 | 광복절 | Every Org. | 2024-09-17 | 추석 | Every Org.
2024-09-16 | 추석 | Every Org. | 2024-09-18 | 추석 | Every Org.
2024-09-17 | 추석 | Every Org. | 2024-10-03 | 개천절 | Every Org.
2024-09-18 | 추석 | Every Org. | 2024-10-09 | 한글날 | Every Org.
2024-10-03 | 개천절 | Every Org. | 2024-12-25 | 크리스마스 | Every Org.
2024-10-09 | 한글날 | Every Org. | 2025-01-01 | 신정(양력설) | Every Org.
2024-12-25 | 크리스마스 | Every Org. | 2025-01-27 | 설 임시공휴일 | Every Org.
2025-01-01 | 신정(양력설) | Every Org. | 2025-01-28 | 설날 연휴 | Every Org.
2025-01-27 | 설 임시공휴일 | Every Org. | 2025-01-29 | 설날 | Every Org.
2025-01-28 | 설날 연휴 | Every Org. | 2025-01-30 | 설날 연휴 | Every Org.
2025-01-29 | 설날 | Every Org. | 2025-03-03 | 대체공휴일(3·1절) | Every Org.
2025-01-30 | 설날 연휴 | Every Org. | 2025-05-01 | 근로자의 날 | Every Org.
2025-03-03 | 대체공휴일(3·1절) | Every Org. | 2025-05-05 | 어린이날 | Every Org.
2025-05-01 | 근로자의 날 | Every Org. | 2025-05-06 | 대체공휴일(부처님 오신날) | Every Org.
2025-05-05 | 어린이날 | Every Org. | 2025-06-03 | 대통령 선거 | Every Org.
2025-05-06 | 대체공휴일(부처님 오신날) | Every Org. | 2025-06-06 | 현충일 | Every Org.
2025-06-03 | 대통령 선거 | Every Org. | 2025-08-15 | 광복절 | Every Org.
2025-06-06 | 현충일 | Every Org. | 2025-10-03 | 개천절 | Every Org.
2025-07-15 | JNPMEDI Office Closing | JNPMEDI | 2025-10-06 | 추석 | Every Org.
2025-08-15 | 광복절 | Every Org. | 2025-10-07 | 추석 연휴 | Every Org.
2025-10-03 | 개천절 | Every Org. | 2025-10-08 | 대체공휴일(추석) | Every Org.
2025-10-06 | 추석 | Every Org. | 2025-10-09 | 한글날 | Every Org.
2025-10-07 | 추석 연휴 | Every Org. | 2025-12-25 | 크리스마스 | Every Org.
2025-10-08 | 대체공휴일(추석) | Every Org. | 2026-01-01 | 새해 | Every Org.
2025-10-09 | 한글날 | Every Org. | 2026-02-16 | 설날 | Every Org.
2025-12-25 | 크리스마스 | Every Org. | 2026-02-17 | 설날 | Every Org.
2025-08-04 | JNPMEDI Office Closing | JNPMEDI | 2026-02-18 | 설날 | Every Org.
2025-10-24 | JNPMEDI Office Closing | JNPMEDI | 2026-03-01 | 삼일절 | Every Org.
2025-11-07 | JNPMEDI Office Closing | JNPMEDI | 2026-03-02 | 삼일절 대체공휴일 | Every Org.
2026-01-01 | 새해 | Every Org. | 2026-05-01 | 근로자의 날 | Every Org.
2026-02-16 | 설날 | Every Org. | 2026-05-05 | 어린이 날 | Every Org.
2026-02-17 | 설날 | Every Org. | 2026-05-24 | 부처님오신날 | Every Org.
2026-02-18 | 설날 | Every Org. | 2026-05-25 | 부처님오신날 대체공휴일 | Every Org.
2026-03-01 | 삼일절 | Every Org. | 2026-06-03 | 전국동시지방선거 | Every Org.
2026-03-02 | 삼일절 대체공휴일 | Every Org. | 2026-06-06 | 현충일 | Every Org.
2026-05-01 | 근로자의 날 | Every Org. | 2026-08-15 | 광복절 | Every Org.
2026-05-05 | 어린이 날 | Every Org. | 2026-08-16 | 광복절 대체공휴일 | Every Org.
2026-05-24 | 부처님오신날 | Every Org. | 2026-09-24 | 추석 | Every Org.
2026-05-25 | 부처님오신날 대체공휴일 | Every Org. | 2026-09-25 | 추석 | Every Org.
2026-06-03 | 전국동시지방선거 | Every Org. | 2026-10-03 | 개천절 | Every Org.
2026-06-06 | 현충일 | Every Org. | 2026-10-05 | 개천절 대체공휴일 | Every Org.
2026-07-15 | JNPMEDI Office Closing | JNPMEDI | 2026-10-09 | 한글날 | Every Org.
2026-08-15 | 광복절 | Every Org. | 2026-12-25 | 크리스마스 | Every Org.
2026-08-16 | 광복절 대체공휴일 | Every Org.
2026-09-24 | 추석 | Every Org.
2026-09-25 | 추석 | Every Org.
2026-10-03 | 개천절 | Every Org.
2026-10-05 | 개천절 대체공휴일 | Every Org.
2026-10-09 | 한글날 | Every Org.
2026-12-25 | 크리스마스 | Every Org.